## Sheet1
| Course | Credits | Prereqs
| CSC 101 | 3
| CSC 111 | 4 | CSC 101
| CSC 211 | 3 | CSC 111
| CSC 215 | 3 | CSC 111 | MAT 301
| CSC 231 | 4 | CSC 111 | MAT 301
| CSC 331 | 3 | CSC 211 | CSC 231
| CSC 350 | 3 | CSC 211
| MAT 206 | 4
| MAT 301 | 4 | MAT 206
| MAT 302 | 4 | MAT 301
| PHY 215 | 4 | MAT 301
| ENG 101 | 3
| ENG 201 | 3 | ENG 101
| SPE 100 | 3
| MMP 100 | 3
| AFN 124 | 3
| PSY 100 | 3
| CRT 100 | 3
Forest | Task | Duration | Prereqs
| Prepare the site | 3
| Set the building footers | 3 | Prepare the site
| Finish the foundation | 5
| Assemble the building | 3 | Finish the foundation
| Interior work | 5 | Assemble the building
| Final building inspection | 15 | Assemble the building | Interior work
| Landscaping | 7 | Interior work
| Driveway paving | 3 | Interior work
| Painting | 2 | Landscaping | Driveway paving
| Arrange the sale | 2 | Final building inspection | Painting
Brighstar | Task | Duration | Prereqs
| Contact and explain | 1
| Obtain approval | 3 | Contact and explain
| Arrange meeting room | 1 | Obtain approval
| Prepare agenda for initial session | 8 | Obtain approval
| Prepare information package | 3 | Prepare agenda for initial session
| Create visual aids | 6 | Prepare agenda for initial session
| Send e-mail to participant | 1 | Arrange meeting room | Prepare information package
| JAD sessions | 7 | Create visual aids | Send e-mail to participant
Bayside | Task | Duration | Prereqs
| Confirm arrangement for training | 3
| Send e-mail to department managers | 1 | Confirm arrangement for training
| Develop training materials | 5 | Confirm arrangement for training
| Copies of handout material | 2 | Develop training materials
| Develop set of powerpoint slides | 5 | Develop training materials
| Practice training session | 2 | Develop set of powerpoint slides
| User Training session | 4 | Copies of handout material | Practice training session